## Projektplanlægger
Gantt Project Planner - Weeks, Overview (Quality Assurance, Otovo group)
[9 empty] | Duration for plan | [5 empty] | Actual startdate |  |  |  |  | % Completion |  |  |  |  | Actual (ud over plan) | [7 empty] | % fuldført (ud over plan)
Responsible | Activity | Start | Duration | Actual Start | Actual Duration | % Completion | Uge 1 (9/2-13/2) |  |  |  |  | Uge 2 (14/2-20/2) | [6 empty] | Uge 3 (21/2-27/3) | [6 empty] | Uge 4 (28/2-6/3) | [6 empty] | Uge 5 (7/3-13/3) | [6 empty] | Uge 6 (14/3-20/3) | [6 empty] | Uge 7 (21/3-27/3) | [6 empty] | Uge 8 (28/3-3/4) | [6 empty] | Uge 9 (4/4-10/4) | [6 empty] | Uge 10 (11/4-17/4) | [6 empty] | Uge 11 (18/4-24/4) | [6 empty] | Uge 12 (25/4-1/5) | [6 empty] | Uge 13 (2/5-8/5) | [13 empty] | Eksamens-periode | [16 empty] | 1. Uge af treugers (2/6-23/6)
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134
All | Samarbejdsaftale | 1 | 1 | 1 | 1 | 100%
All | First contact with Supervisor | 1 | 7 | 1 | 3 | 100% | bar: Uge 2 (14/2-20/2) 7
All | Assess articles sent by supervisor | 8 | 5 | 13 | 2 | 100%
All | Draft of Gantt-chart | 8 | 8 | 8 | 8 | 100%
All | Læringsmål(egne) | 8 | 8 | 15 | 1 | 100%
All | Project Canvas | 8 | 8 | 8 | 8 | 100%
All | Projektbeskrivelse | 8 | 8 | 14 | 2 | 100%
All | In-depth Research OCR(STR) and STR(scene text recognition) models | 15 | 15 | 15 | 15 | 100%
All | 1. implementation of retrained recognition model using HPC (including learning HPC) | 22 | 30 | 31 | 50 | 100%
Michael | Data Analysis(1. data dump) | 34 | 5 | 34 | 5 | 100%
Michael | Research influence of resolution on accuracy | 34 | 5 | 34 | 5 | 100%
All | Mid-way report | 38 | 12 | 41 | 9 | 100%
All | Give peer review to other projects | 50 | 5 | 52 | 3 | 100%
Khalil | Label bounding boxes (1. data dump) | 69 | 4 | 69 | 4 | 100%
Mathias | Re-train CRAFT (on 1. data dump) | 73 | 40 | 85 |  | 50%
Khalil | Label bounding boxes (2. data dump) | 77 | 25 | 85 | 20 | 100%
Michael | Data Analysis (2. data dump) | 85 | 1 | 85 |  | 100%
Khalil | 2. implementation of retrained recognition model using HPC | 97 | 7 | 110 | 7 | 100%
Michael | Compare different solutions (STD + OCR) | 97 | 20 | 110 | 20 | 100%
Michael | Learning Weights & Biases | 85 | 25 | 85 | 25 | 100%
Mathias | Re-train CRAFT (on 2. data dump) | 113 | 10 | 113 | 12 | 50%
Mathias | Bayesian Optimization on Recognition models | 125 | 10 | 113 | 10 | 0%
Khalil | Re-train CRAFT on all data | 125 | 12 | 125 | 10 | 50%
All | Analyze strengths and weaknesses of prototype | 113 | 3 | 113 | 3 | 100%
Michael | Barcode scanning | 114 | 5 | 114 | 4 | 100%
All | Final prototype | 113 | 5 | 113 | 14 | 80%
All | Project writing | 38 | 100 | 38 | 110 | 100%
All | Video Pitch | 120 | 10 | 126 | 1 | 60%